## LOG-TIME SPENT ON WHAT
ACTION | TIME SPENT IN HOURS | DATE | TOTAL TIME SPENT
RESEARCHING ( Planning functionality, researching web) | 2 | 2020-04-17 | 25 | h | `0
2020-04-18
Working on Navbar - need to center search bar and modify buttons right | 2 | 2020-04-19
Navbar completly reworked without bootstrap - excluded searchbar would be somewhere else. | 4 | 2020-04-20
Added reactive navbar hamburger icon, for mobile users | 2 | 2020-04-21
Stated implementing logic, connected to PostgresSQL database, Made Article/Category classes. | 3 | 2020-04-22
Added 3 recortds to database manually foreach for showing on screen - Next -- Need to think through the Article class and (remove bad properties and add new ones) | 2 | 2020-04-23
Formatted article and whole index page, looks nice, still need to research about adding image to class - on disc - commited to program time ago function | 5 | 2020-04-24
Added GetTimeAgo method for article class, implemented full up until a year | 3 | 2020-04-25
Reformated article a bit, text etc. Still need to implement images somehow | 2 | 2020-04-26
2020-04-27
2020-04-28
2020-04-29
2020-04-30
2020-05-01
2020-05-02
2020-05-03
2020-05-04
2020-05-05
2020-05-06
2020-05-07
2020-05-08
2020-05-09
2020-05-10
2020-05-11
2020-05-12
2020-05-13
2020-05-14
2020-05-15
2020-05-16
2020-05-17
2020-05-18
2020-05-19
2020-05-20
2020-05-21
2020-05-22
2020-05-23
2020-05-24
2020-05-25
2020-05-26
2020-05-27
2020-05-28
2020-05-29
2020-05-30
2020-05-31
2020-06-01
2020-06-02
2020-06-03
2020-06-04
2020-06-05
2020-06-06
2020-06-07
2020-06-08
2020-06-09
2020-06-10
2020-06-11
2020-06-12
2020-06-13
2020-06-14
2020-06-15
2020-06-16
2020-06-17
2020-06-18
2020-06-19
2020-06-20
2020-06-21
2020-06-22
2020-06-23
2020-06-24
2020-06-25
2020-06-26
2020-06-27
2020-06-28
2020-06-29
2020-06-30
2020-07-01
2020-07-02
2020-07-03
2020-07-04
2020-07-05
2020-07-06
2020-07-07
2020-07-08
2020-07-09
2020-07-10
2020-07-11
2020-07-12
2020-07-13
2020-07-14
2020-07-15
2020-07-16
2020-07-17
2020-07-18
2020-07-19
2020-07-20
2020-07-21
2020-07-22
2020-07-23
2020-07-24

## PLAN
https://www.budibase.com/blog/how-to-make-a-web-app/
| XX | DATE | P
IDEATION | 1. Source an idea | 2020-04-17 | Search for fitting concept for static page with little to no JS
| 2. Market research | 2020-04-17 | x
| 3. Define functionality | 2020-04-17 | FUNCTIOONALITY TAB
DESIGN | 4. Sketch your web app | 2020-04-20 | Parialy done
| 5. Plan your workflow | 2020-04-18 | Step by step
| 6. Wireframe the UI | 2020-04-20 | step by step | 123
7. Seek early validation
DEVELOPMENT | 8. Architect your database
9. Develop your frontend
10. Build your backend
LAUNCH | 11. Host your web app
12. Deploy your web app

## WORKFLOW
L.P | TO DO | DATE START | DATE END | DONE ?
1 | Do navigation bar from scratch for mobile and pc (21.04 adding dropdown for mobile) | 2020-04-19 | 2020-04-20 | YAS
2 | Start implementing articles, class, functions, start displaying by fetching data from memory, | 2020-04-22 | 2020-04-23 | YAS
3 | Reforge Article class - add author, Article Type ? (to change css/html order ?) Comments number. | 2020-04-23 | 2020-04-26 | YAS
4 | Apply styling for article class (index page) | 2020-04-26 | 2020-04-26 | YAS
5 | Need to format whole article to look nice and get the Time ago method for article class :) | 2020-04-26 |  | NO
6 |  |  |  | NO
7 |  |  |  | NO
8 |  |  |  | NO
9 |  |  |  | NO
10 |  |  |  | NO
11 |  |  |  | NO
12 |  |  |  | NO
13 |  |  |  | NO
14 |  |  |  | NO
15 |  |  |  | NO
16 |  |  |  | NO
17 |  |  |  | NO
18
19

## DATETIME
1 | MINUTA | TEMU | 1 | GODZINA | 1 | dzien | 1 | tydzine | 1 | miesiac
2 | MINUTY | TEMU | 2 | GODZINY | 2 | dni | 2 | tygodnie | 2 | miesiace
3 | MINUTY | TEMU | 3 | GODZINY | 3 | dni | 3 | tygodnie | 3 | miesiace
4 | MINUTY |  | 4 | GODZINY | 4 | dni | 4 | tygodnie | 4 | miesiace
5 | MINUT |  | 5 | GODZIN | 5 | dni | 5 | tygodnie | 5 | miesiecy
6 | MINUT |  | 6 | GODZIN | 6 | dni
7 | MINUT |  | 7 | GODZIN | 7 | dni
8 | MINUT |  | 8
9 | MINUT |  | 9
10 | MINUT |  | 10
11 | MINUT |  | 11
12 | MINUT |  | 1
13 |  |  | 2
14 |  |  | 21
22
23
24

## FUNCTIONALITY
ID | Expected functionality | IMPORTANCE LEVEL | WORKED ON ? | STATUS | DATE IMPLEMENTED
1 | USER CAN LOG IN VIA REGISTER TAB (blazor popup some time) | 1 | NO | NOT DONE
2 | USER CAN RETRIEVE AND CHANGE PASSWORD | 2 | NO | NOT DONE
3 | USER CAN GIVE INFO ABOUT DEALS BY BUTTON IN NAV BAR (point upps) | 1 | NO | NOT DONE
4 | USER CAN FILTER MAIN PAGE WITH DEALS BY CATEGORY | 1 | NO | NOT DONE
5 | USERS CAN CHAT BELOW EACH DEAL(Disqus app) | 3 | NO | NOT DONE
6 | ADMIN CAN CREATE DEALS ON MAIN PAGE | 1 | NO | NOT DONE
7 | USER CAN HIPERLINK TO WEBSITE WITH DEAL | 1 | NO | NOT DONE
8 |  |  | NO | NOT DONE
9 |  |  | NO | NOT DONE
10 |  |  | NO | NOT DONE
11 |  |  | NO | NOT DONE
12 |  |  | NO | NOT DONE
13 |  |  | NO | NOT DONE
14 |  |  | NO | NOT DONE
15 |  |  | NO | NOT DONE
16 |  |  | NO | NOT DONE
1- High, 2-Medium, 3- LOW

## SKETCHES OF WEBSITE
COLOR PALLETTE
#142850
#27496d
#0c7b93
#00a8cc
<nav class="navbar navbar-expand-sm navbar-toggleable-sm navbar-light bg-white border-bottom box-shadow mb-3">
<div class="container">
<a class="navbar-brand" asp-area="" asp-page="/Index">DEVPAGE</a>
<button class="navbar-toggler" type="button" data-toggle="collapse" data-target=".navbar-collapse" aria-controls="navbarSupportedContent"
aria-expanded="false" aria-label="Toggle navigation">
<span class="navbar-toggler-icon"></span>
</button>
<div class="navbar-collapse collapse d-sm-inline-flex flex-sm-row-reverse">
<ul class="navbar-nav flex-grow-1">
<li class="nav-item">
<a class="nav-link text-dark" asp-area="" asp-page="/Index">Home</a>
</li>
<li class="nav-item">
<a class="nav-link text-dark" asp-area="" asp-page="/Privacy">Privacy</a>
</li>
</ul>
</div>
</div>
</nav>